## Instructions
Ohio Accreditation Support Project ¦ Work Plan Template Instructions
Purpose and Application
This work plan is intended to provide local health jurisdictions with a mechanism for planning and tracking major milestones toward achieving public health agency accreditation through the Public Health Accreditation Board (PHAB). This plan will assist with tracking statewide, aggregate progress toward assuring that all residents receive services from an accredited organization. Agencies who are in 'not yet started' or 'pre-application' phases of accreditation as of April 30, 2017 are required by the Ohio Department of Health to submit a work plan. Agencies that have already applied to PHAB and those that are already accredited are not required to submit a work plan. Agencies with existing work plans may choose to submit those plans in lieu of this template, and are asked to incorporate the milestones from this template in their work plans if they do so.
Instructions for Use
This template can be retrieved from the Accreditation Support Project website: https://u.osu.edu/cphpaccreditationproject/ (see work plan tab). Read the instructions and familiarize yourself with the remaining tabs (the sample timeline, template, and example work plan) before starting. Fill in the information that appears in red font the first time you complete the work plan, then update this in subsequent reporting periods only as needed. Use the requested format for dates and use the drop down boxes to indicate the status of each milestone (Not Started, In Progress, or Completed) as of the time period. For milestones with a status of Not Started or In Progress, select a target completion date. If this target changes during a subsequent reporting period, complete the "Rev Target Completion" (revised) column. The "Lead" column is for your use only and is meant to help you assign responsibility for each milestone. There is a key to the template to the right of the table itself. The shared services milestones are optional; they are intended to assist agencies that are pursuing shared arrangements to support their PHAB documentation. Ohio's public health departments are required to be accredited by July 2020, however those considering consolidation or mergers have until July 2021; this template provides tracking through 2021 for those agencies for which this applies.
How & When to Submit
Save the completed work plan using the following naming convention (no abbreviations): Agency Name Work Plan Month Year (Example: Mytown Health District Work Plan April 2017). Save a copy of the completed work plan for yourself and upload a copy to the Ohio Profile and Performance Database (OPPD) under Domain 11 (Maintain Administrative and Management Capacity). Completed work plans are due in April 30 and October 31 of each year. Agencies that have an existing work plan serving as a guide for their accreditation preparation: In lieu of submitting this work plan, you may incorporate the milestones shown here and submit your existing plan using these same instructions.
Notes
Milestones within this template in no way represent all of the work/related documentation required by PHAB. The achievement of these selected milestones may not occur sequentially and the time needed to prepare and write pre-requisite documents and to select, review, and prepare other required documentation should not be underestimated. Shared services dialogue and negotiations may also be time-intensive. The Center for Public Health Practice does not represent of speak on behalf of PHAB. Visit the PHAB website for more detailed information about the accreditation process: www:PHABoard.org. Completion and submission of work plan, for applicable agencies, are tied to access to free training and TA provided through this project.
Contact
For questions, please contact the Center for Public Health Practice at 614-292-2291 or practice@cph.osu.edu.
2017-03-29

## Example Work Plan
Ohio LHD Accreditation Readiness & Shared Services Planning Work Plan Template
Last Updated: 10/31/2017
| Agency Name: | Mytown Health District
| Primary Contact Name: | Ima Xample
| Phone: | ###-###-####
| Email: | imaxample@mytownhealth.xxx
| Selected Milestones | Status 2016 | Target Completion | Rev Target Completion | Lead | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | Updates/Notes | Key
[6 empty] | Apr | Oct | Apr | Oct | Apr | Oct | Apr | Oct | Apr | Oct
1 | Budget for costs of applying for accreditation | Complete |  |  |  | Complete | Complete
2 | Health Department has designated internal Accreditation Team | Complete |  |  |  | Complete | Complete
3 | Internal communications plan to keep staff & community leaders informed of progress toward accreditation | Complete |  |  |  | Complete | Complete | [9 empty] | Time & Target
4 | Complete "self assessment" to review standards, measures, & required documentation | Complete |  |  |  | Complete | Complete | [9 empty] | 2016: status as of 12/31/2016
5 | Completion of prerequisite: Community Health Assessment (CHA) [PHAB Std 1.1] | Complete |  |  |  | Complete | Complete | [9 empty] | Target Completion: estimated completion if Not Started or In Progress (does not change)
6 | Completion of prerequisite: Community Health Improvement Plan (CHIP) [PHAB Std 5.2] | Complete |  |  |  | Complete | Complete | [9 empty] | REV Target Completion: revised estimated completion, if needed
7 | Completion of prerequisite: Strategic Plan (SP) [PHAB Std 5.3] | In Progress | 2017-06-30 |  | IX | Complete | Complete | [9 empty] | Apr: as of April in given year
8 | Completion of prerequisite: Communication & branding strategy [PHAB Std 3.2] | Complete |  |  |  | Complete | Complete | [9 empty] | Oct: as of October in given year
9 | Completion of prerequisite: Emergency Operations Plan (EOP) [PHAB Std 5.4] | Complete |  |  |  | Complete | Complete | [9 empty] | Status
10 | Completion of prerequisite: Workforce Development Plan [PHAB Std 8.2] | Not Started | 2017-07-31 | 2017-11-30 | MC | In Progress | In Progress | [10 empty] | Not Started: | Not Started
11 | Completion of prerequisite: Quality Improvement Plan [PHAB Std 9.2] | Not Started | 2017-11-30 |  | AN | Not Started | In Progress | [10 empty] | In Progress: | In Progress
12 | Completion of prerequisite: Performance Management System [PHAB Std 9.1] | In Progress | 2017-06-30 |  | AN | In Progress | Complete | [10 empty] | Complete: | Complete
13 | Submit application | Not Started | 2017-12-31 |  | IX | Not Started | Not Started
14 | Gain access to e-PHAB after Accreditation Coordinator training | Not Started | 2018-03-31 |  | IX | Not Started | Not Started
15 | Submit documentation | Not Started | 2019-03-31 |  | IX | Not Started | Not Started | [9 empty] | Target accdg to sample timeline
16 | Site visit completed | Not Started | 2019-11-30 |  | IX | Not Started | Not Started
17 | Accreditation decision communicated to health department | Not Started | 2020-03-30 |  | IX | Not Started | Not Started | [9 empty] | Lead
Initials of lead staff
For those considering new shared service arrangements:
18 | Identify services that may benefit from shared services/consolidation | In Progress |  |  | FH | Complete | Complete
19 | Identify potential shared service/LHD consolidation partners | In Progress |  |  | FH | Complete | Complete
20 | Engage external assistance, as appropriate (facilitation, research, expertise, etc.) | Not Started |  |  | JH | In Progress | In Progress
21 | Hold discussions with potential partners | Not Started |  |  | JH | In Progress | In Progress
22 | Reach decision to proceed or not to proceed | Not Started |  |  | JH | Not Started | Not Started
22 | Reach written/formal agreement on shared service and/or consolidation arrangement,if applicable | Not Started |  |  | JH | Not Started | Not Started
23 | Implement new shared service/consolidation arrangement, if applicable | Not Started |  |  | JH | Not Started | Not Started

## Work Plan Template
Ohio LHD Accreditation Readiness & Shared Services Planning Work Plan Template
Last Updated: mm/dd/yyyy
Agency Name:
Primary Contact Name:
Phone:
Email:
| Selected Milestones | Status 2016 | Target Completion | Rev Target Completion | Lead | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | Updates/Notes | Key
[6 empty] | Apr | Oct | Apr | Oct | Apr | Oct | Apr | Oct | Apr | Oct
1 | Budget for costs of applying for accreditation
2 | Health Department has designated internal Accreditation Team
3 | Internal communications plan to keep staff & community leaders informed of progress toward accreditation | [15 empty] | Time & Target
4 | Complete "self assessment" to review standards, measures, & required documentation | [15 empty] | 2016: status as of 12/31/2016
5 | Completion of prerequisite: Community Health Assessment (CHA) [PHAB Std 1.1] | [15 empty] | Target Completion: estimated completion if Not Started or In Progress (does not change)
6 | Completion of prerequisite: Community Health Improvement Plan (CHIP) [PHAB Std 5.2] | [15 empty] | REV Target Completion: revised estimated completion, if needed
7 | Completion of prerequisite: Strategic Plan (SP) [PHAB Std 5.3] | [15 empty] | Apr: as of April in given year
8 | Completion of prerequisite: Communication & branding strategy [PHAB Std 3.2] | [15 empty] | Oct: as of October in given year
9 | Completion of prerequisite: Emergency Operations Plan (EOP) [PHAB Std 5.4] | [15 empty] | Status
10 | Completion of prerequisite: Workforce Development Plan [PHAB Std 8.2] | [16 empty] | Not Started: | Not Started
11 | Completion of prerequisite: Quality Improvement Plan [PHAB Std 9.2] | [16 empty] | In Progress: | In Progress
12 | Completion of prerequisite: Performance Management System [PHAB Std 9.1] | [16 empty] | Complete: | Complete
13 | Submit application
14 | Gain access to e-PHAB after Accreditation Coordinator training
15 | Submit documentation | [15 empty] | Target accdg to sample timeline
16 | Site visit completed
17 | Accreditation decision communicated to health department | [15 empty] | Lead
Initials of lead staff
For those considering new shared service arrangements:
18 | Identify services that may benefit from shared services/consolidation
19 | Identify potential shared service/LHD consolidation partners
20 | Engage external assistance, as appropriate (facilitation, research, expertise, etc.)
21 | Hold discussions with potential partners
22 | Reach decision to proceed or not to proceed
23 | Reach written/formal agreement on shared service and/or consolidation arrangement, if applicable
24 | Implement new shared service/consolidation arrangement, if applicable

## Sample Timeline
Instructions, Template, template example, sample timelinedfd